## Sheet1
Risk Title | Description | Estimated likelihood of occurrence (1-5 or H/M/L) | Estimated Impact (1-5 or H/M/L) | Estimated retirement Cost | priority | responsible engineer | target completion date | detailed plan
Team communication | Newly formed team need more communication | 3 | 3 | 9 | 2 | All Members | 2018-02-01 | Share thoughts through wechat and slack
Feature Design | Some essential features are still vague | 4 | 4 | 16 | 1 | All Members | 2018-02-08 | Extra meeting in 2/7
Large Datasets | Large datasets decrease loading efficiency | 4 | 3 | 12 | 2 | He Yu, Bowen Jiang | 2018-03-08 | Using more efficient query method/ mysql
Connect backend and front end | Front end have issues using services from back end | 5 | 4 | 20 | 1 | All Members | 2018-03-20 | Using peer programing with both back end and front end programmers
Web page refresh | Create a new page is unnecessary after login page | 4 | 2 | 8 | 3 | Bowen Jiang | 2018-03-20 | Using AJax to refresh page after login
Testing issue | Most team members are not familiar with testing methods and techniches | 4 | 5 | 20 | 1 | All Members | 2018-04-20 | Learn Junit and each member should design several test cases
Deployment rush | May have no enough time to make the project full project deployed | 4 | 4 | 16 | 1 | All Members | 2018-04-29 | Update all the source codes to github, and finish the test, then deploy the web app