## Bowen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/22 - 1/26) | 4 | 2 | 2 | 0,1,6 | 2 | 1 |  |  |  |  | 1 | 0,1,6 | 4
2 (1/29 - 2/2) | 4 | 2 | 2 | 0,1,6 | 2 | 1 |  |  |  |  | 1 | 0,1,6 | 6
3 (2/5 - 2/9) | 8 | 4 | 4 | 0 - learning how to write configuration management plan, 1 - Discuss the key features of our app, 5 - Distinguish several roles of our group members | 2 | 1 |  |  |  |  | 1 | 2,3 | 8
4(2/12 - 2/16) ill | 0
5(2/19 - 2/23) | 6 | 2 | 4 | 0 - learning our website framework, setting up DE 2 - design our databse 6 - Find food data for our website | 2 | 1 |  |  |  |  | 1 | 0
6(2/26 - 3/2) | 4 | 2 | 2 | 0 - learning mysql | 2 | [6 empty] | 0,3 | 4
8(3/12 - 3/16) | 4 | 2 | 2 | 0 - Learning mysql, spring mvc framework 3 - Implement our project | 1 |  |  | 1 |  |  |  | 0,3 | 4
10(3/26 - 3/30) | 10 | 4 | 6 | 0 - learning ajax, jquery and mysql 2 - design our food database 3 - implement food recommendation, login, signup | 4 |  | 1 | 1 |  |  |  | 0,3 | 6

## Huaze
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1.22~1.25 | 3 | 1 | 2 |  | 0.5 |  |  | 0 | 0 | 0.5 | 0
1.25~2.1 | 5.5 | 3.5 | 2 |  | 1 | 0.5 | 1 | 0 | 0 | 1 | 0
2.2~2.8 | 7 | 3 | 4 |  | 1 | 0.5 | 0.5 | 0 | 0 | 1 | 0
2.9~2.15 | 6 | 4 | 2 |  | 1 | 1 | 1 | 0 | 0 | 1 | 0
2.16~2.22 | 11 | 9 | 2 |  | 1 | 2 | 1 | 4 | 0 | 1 | 0
2.23~3.1 | 8.5 | 6.5 | 2 | 0 - Restful API 2 - Our architecture 3 - Redesign the service and DAO layer | 1 | 0.5 | 2 | 2 | 0 | 1 | 0
3.11~3.15 | 7 | 5 | 2 | 0 - JDBC 2 - Refine our structure 3 - Connect the front-end and back-end 5 - Explain to others how to implement the method in our architecture | 1 | 0 | 1 | 2 | 0 | 1 | 0
3.16~3.22 | 7 | 5 | 2 |  | 1 | 0 | 1 | 2 | 0 | 1 | 0
3.23~3.29 | 6 | 4 | 2 |  | 1 | 0 | 0 | 2 | 0 | 1 | 0
3.30~4.5 | 6 | 4 | 2 |  | 1 | 0 | 1 | 1 | 0 | 1 | 0
4.6~4.12 | 6 | 4 | 2 |  | 1 | 0 | 1 | 1 | 0 | 1 | 0
4.13~4.19 | 7 | 5 | 2 |  | 1 | 1 | 1 | 1 | 0 | 1 | 0
4.20~4.26 | 7 | 5 | 2 |  | 1 | 0 | 2 | 1 | 0 | 1 | 0

## Chenyang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1.22-1.26 | 3 | 1 | 2 | 0,5 | 1 |  |  |  |  | 2 |  | 0,5 | 5
1.29-2.2 | 5 | 3 | 2 | 0,5 | 3 |  |  |  |  | 2 |  | 0,5 | 6
2.2-2.8 | 8 | 2 | 4 | 0,2,5 | 2 |  | 2 |  |  | 4 |  | 0,2,5 | 8
2.8-2.15 | 6 | 2 | 4 | 0,1,2,5 | 1 | 1 | 2 |  |  | 2 |  | 0,1,2,5 | 6
2.19-2.23 | 10 | 6 | 2 | 0,2,3,4,5 | 1 |  | 4 | 2 | 1 | 2 |  | 0,2,3,4,5 | 10
2.26-3.2 | 12 | 6 | 2 | 0,2,3,4,5 | 1 |  | 6 | 2 | 1 | 2 |  | 0,2,3,4,5 | 12
3.12-3.16 | 8 | 6 | 2 | 0,2,3,4,5 | 1 | 1 | 1 | 1 | 2 | 2 |  | 0,2,3,4,5 | 10
3.19 - 3.23 | 8 | 6 | 2 | 0,2,3,4,5 | 1 |  | 2 | 1 | 2 | 2 |  | 0,2,3,4,5 | 10
3.26-3.30 | 8 | 4 | 4 | 0,2,3,4,5 | 1 |  | 2 | 1 | 2 | 2 |  | 0,2,3,4,5 | 8
4.2-4.6 | 6 | 4 | 2 | 0,2,3,4,5 | 1 |  | 1 |  | 2 | 2 |  | 0,2,3,4,5 | 6
4.9-4.13 | 6 | 4 | 2 | 0,2,3,4,5 | 1 |  | 1 |  | 2 | 2 |  | 0,2,3,4,5 | 6
4.16-4.20 | 8 | 6 | 2 | 0,2,3,4,5 | 2 |  | 2 |  | 2 | 2 |  | 0,2,3,4,5 | 8
4.23-4.27 | 16 | 12 | 4 | 4,5,6 |  |  |  |  | 6 | 3 | 3 | 6 | 8

## Fengbo
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/22/2018 - 1/26/2018 | 2 |  | 2 | 5 | [5 empty] | 2
1/29/2018 - 2/2/2018 | 7 | 5 | 2 | 0,5 | 5 |  |  |  |  | 2
2/5/2018 - 2/9/2018 | 9 | 5 | 4 | 0,1,5 | 2 | 3 |  |  |  | 4
2/12/2018 - 2/16/2018 | 8 | 6 | 2 | 0,2,5 | 2 |  | 4 |  |  | 2
2/19/2018 - 2/23/2018 | 7 | 5 | 2 | 0,1,2,5 | 1 | 2 | 2 |  |  | 2
2/26/2018 - 3/2/2018 | 6 | 4 | 2 | 0,2,5 | 2 |  | 2 |  |  | 2
3/12/2018 - 3/16/2018 | 6 | 4 | 2 | 0,3,5 | 2 |  |  | 2 |  | 2
3/19/2018 - 3/23/2018 | 8 | 6 | 2 | 0,3,5 | 3 |  |  | 3 |  | 2
3/26/2018 - 3/30/2018 | 9 | 5 | 4 | 0,3,5 | 1 |  |  | 4 |  | 4
4/2/2018 - 4/6/2018 | 6 | 4 | 2 | 0,3,5 | 2 |  |  | 2 |  | 2
4/9/2018 - 4/13/2018 | 4 | 2 | 2 | 0,5 | 2 |  |  |  |  | 2
4/16/2018 - 4/20/2018 | 2 | 2 | 0 | 0 | 2 |  |  |  |  | 0
4/23/2018 - 4/27/2018 | 8 | 4 | 4 | 0,4,5 | 2 |  |  |  | 2 | 4

## He
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1(1/18 - 1/25) | 4 | 2 | 2 | 0- reading lecture notes | 2 | [6 empty] | 2 | 4
week 2(1/25 - 2/1) | 7 | 5 | 2 | 0-reading material; assignments | 3 | [6 empty] | 4 | 6
week 3(2/1 - 2/8) | 8 | 4 | 4 | 0 - reviewing lecture; 1 - analize featuer and prepare presentation | 2 | 2 | [5 empty] | 4 | 6
week 4(2/8 - 2/15) | 4 | 2 | 2 | 0 - reading lecture notes; 1 - review SPPP | 1 | 1 | [5 empty] | 4 | 6
week 5(2/19 - 2/23) | 6 | 4 | 2 | 0- review lecture notes; 2- build database | 2 |  | 2 |  |  |  |  | 8 | 10
week 6(2/26 - 3/2) | 8 | 6 | 2 | 0 -Intellij tutorial; 3- import data to Mysql | 2 |  |  | 3 |  |  |  | 6 | 6
week 7(3/12 - 3/16) | 6 | 4 | 2 | 0- review lecture notes; 3 - writing Mysql script | 2 |  |  | 2 |  |  |  | 6 | 8
week 8(3/19 - 3/23) | 6 | 6 | 2 | 0- homework; 3 - read user data to database | 4 |  |  | 2 |  |  |  | 6 | 8
week 9(3/26 - 3/30) | 12 | 8 | 4 | 3 - add feature |  |  |  | 8 |  |  |  | 6 | 8
week10(4/2 - 4/6) | 6 | 4 | 2 | 3 - add food tags to data; 4 - design test cases |  |  |  | 3 | 1 |  |  | 6 | 8
week11(4/9 - 4/13) | 8 | 6 | 2 | 1- re-analysis requirement; 5 - refine document |  | 2 |  |  |  | 4 |  | 8 | 10
week 12(4/16 - 4/20) | 8 | 6 | 2 | 4- integration test design; 5 - refine document |  |  |  |  | 4 | 2 |  | 10 | 12
week 13(4/23 - 4/27) | 16 | 12 | 4 | 4 - integration test; 5 - document; group presentation ppt |  |  |  |  | 6 | 3 | 3 | 6 | 8

## Midterm Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | Proposal and Planning Document (SPPP) | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Huaze Sang | Wrote 3 user stories | Responsible for requirement part |  |  | Contribute to the iteration 0 and iteration 1 presentation | Contribute 2 important commits on github |  | Build our configuration of server and database, make the web application runnable on Tomcat server. | Come up with ideas about what we are going to do, how to implement that, which framework to use
Bowen Jiang | Wrote 3 user stories | Responsible for configuration management |  |  | Contribute to iteration 0 presentation | Set up our team repository |  |  | Setup weekly meeting and workload, monitor development process | Finding data for our food recommenadtion and calories calculation
He Yu | Wrote 3 user stories | Responsible for process control |  |  | Contribution to iteration 0 presentation | Haven't upload on Github yet |  |  | Remind team with weekly process, documentation and workload; | Setting up Mysql and setting data for the project
Fengbo Gao | Wrote 7 user stories | Responsible for security |  |  | Contribution to iteration 0 presentation | Haven't upload on Github yet |  |  | Come up with ideas about front-end
Chenyang Li | Wrote 3 user stories | Responsible for the front-end design |  |  | Contribution to iteration 0 presentation and iteration 1 presentation | Haven't upload on Github yet |  | Build the front-end web page: Home page, login page, sign-up page | Come up with ideas about front-end and do the basic design | Need to figure out how to relate the front-end to the back-end

## Final Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
He Yu | user stories; manage the process and documents | wrote class and methods, key algorithms; | Wrote almost whole document | contributes to iteration0, 2 and 3 presentation; | data script; tests | Integration test using selenium; | Add depencies for json-simple | Process management | risk_report; meeting minutes; refine documents;
Chenyang Li |  | wrote class and algorithms |  | contributes to iteration0, 1 and 3 presentation; | contributes to the whole front-end design and some js codes for relating front-end and back-end |  |  | UI design management | meeting minutes, refine documents
Fengbo Gao |  | wrote design pattern | wrote user case | contributes to iteration0, 2 and 3 presentation; | userpage(uncompleted) | unit test(model) |  | Security management | meeting minutes, refine documents, come up idea of this project
Bowen jiang | Write and retire user stories |  |  | contributes to iteration 0, 2 and 3 presentations | data script, back end and front-end javascript |  |  | Communication and progress management | Meeting minutes, refining documents, features disscussion
Huaze Sang | create several user stories | Design our back-end framework and implement it, help design our front end stracture |  | contributes to iteration 0, 1 and 3 presentations | implement our back-end framework and help others to build our front-end page | write a little test cases | deployed our project on digital ocean | Design management | Meeting minutes